## Insight
C.N.Issue Date/Time | Prefix | Promoter Reference | Notice Type | Start | End | Date Diff | Works Status | Phase Duration | Days Late | Early Start? | Notifiable Organisation Name | Site Status | Traffic Management | Description | Address 1 | Address 2 | Reinst. Cat C/W | Phase Type | Phase | Seq.No. | Current Notification Type | Notice Works Type Desc. | Notifiable District Name | Surface Location | Excavation Type | Street T/S? | Town | Alternative Town | Application Status | Permit? | Works Clear Date | Inspection Units | Works T/S? | Actual Start Date | Out of Hours / Env. Health Notified? | Notice Duration | Late Start? | Hrs Late | Early/Late Start? | Northing | Easting | Actual Start Time
2016-07-08 13:17 | AD031 | 52697044 | WORKS STOP | 2016-07-05 | 2016-07-07 | 2 | WORKS CLOSED | 3 |  | N | NORFOLK COUNTY COUNCIL | SITE PERMANENT | ROAD CLOSURE | Repair leak on 6' AC | PORINGLAND ROAD | STOKE HOLY CROSS | CARRIAGEWAY TYPE 4 - UP TO 0.5 MS | ASSET ACTIVITY & REINSTATEMENT IF REQD | 1 | 2 | WORKS STOP | IMMEDIATE (URGENT) | SOUTH NORFOLK | CW | EXCAVATION WORKS - OTHER | Y | STOKE HOLY CROSS |  | Granted | Y | 2016-07-07 | 1 | Y | 2016-07-05 | N | 3 | N |  | N | 302612.05 | 625962.06 | 10:30
2017-11-21 13:24 | AD031 | 54211991 | WORKS STOP | 2017-11-14 | 2017-11-20 | 6 | WORKS CLOSED | 5 |  | N | NORFOLK COUNTY COUNCIL | SITE PERMANENT | ROAD CLOSURE | repair visible leak | LONG LANE | STOKE HOLY CROSS | CARRIAGEWAY TYPE 4 - UP TO 0.5 MS | ASSET ACTIVITY & REINSTATEMENT IF REQD | 1 | 4 | WORKS STOP | IMMEDIATE (URGENT) | SOUTH NORFOLK | CW | EXCAVATION WORKS - OTHER | Y | STOKE HOLY CROSS |  | Granted | Y | 2017-11-20 | 1 | Y | 2017-11-14 | N | 5 | N |  | N | 302289.23 | 625037.68 | 14:30
2017-12-27 11:55 | AD031 | 54393545 | WORKS STOP | 2017-12-19 | 2017-12-22 | 3 | WORKS CLOSED | 4 |  | N | NORFOLK COUNTY COUNCIL | SITE PERMANENT | ROAD CLOSURE | Burst main | LONG LANE | STOKE HOLY CROSS | CARRIAGEWAY TYPE 4 - UP TO 0.5 MS | ASSET ACTIVITY & REINSTATEMENT IF REQD | 1 | 3 | WORKS STOP | IMMEDIATE (EMERGENCY) | SOUTH NORFOLK | VG | EXCAVATION WORKS - OTHER | Y | STOKE HOLY CROSS |  | Granted | Y | 2017-12-22 | 1 | Y | 2017-12-19 | N | 4 | N |  | N | 302083.7 | 624258.22 | 11:30
2020-07-01 16:07 | AD031 | 57615673 | WORKS STOP | 2020-06-26 | 2020-07-01 | 5 | WORKS CLOSED | 4 |  | N | NORFOLK COUNTY COUNCIL | SITE PERMANENT | ROAD CLOSURE | mains repairs | LONG LANE | STOKE HOLY CROSS | CARRIAGEWAY TYPE 4 - UP TO 0.5 MS | ASSET ACTIVITY & REINSTATEMENT IF REQD | 1 | 3 | WORKS STOP | IMMEDIATE (URGENT) | SOUTH NORFOLK | CW | EXCAVATION WORKS - OTHER | Y | STOKE HOLY CROSS |  | Granted | Y | 2020-07-01 | 1 | Y | 2020-06-26 | N | 4 | N |  | N | 302118.93 | 624339.26 | 9:00
2021-02-17 08:56 | AD031 | 58556008 | WORKS STOP | 2021-02-10 | 2021-02-16 | 6 | WORKS CLOSED | 5 |  | N | NORFOLK COUNTY COUNCIL | SITE PERMANENT | ROAD CLOSURE | mains repair | LONG LANE | STOKE HOLY CROSS | CARRIAGEWAY TYPE 4 - UP TO 0.5 MS | ASSET ACTIVITY & REINSTATEMENT IF REQD | 1 | 4 | WORKS STOP | IMMEDIATE (URGENT) | SOUTH NORFOLK | CW | EXCAVATION WORKS - OTHER | Y | STOKE HOLY CROSS |  | Granted | Y | 2021-02-16 | 1 | Y | 2021-02-10 | N | 5 | N |  | N | 301864.68 | 624000.71 | 15:30
2021-03-17 08:54 | AD031 | 58713993 | WORKS STOP | 2021-03-10 | 2021-03-16 | 6 | WORKS CLOSED | 5 |  | N | NORFOLK COUNTY COUNCIL | SITE PERMANENT | ROAD CLOSURE | mains repair | CHANDLER ROAD | STOKE HOLY CROSS | CARRIAGEWAY TYPE 4 - UP TO 0.5 MS | ASSET ACTIVITY & REINSTATEMENT IF REQD | 1 | 4 | WORKS STOP | IMMEDIATE (URGENT) | SOUTH NORFOLK | CW | EXCAVATION WORKS - OTHER | N | STOKE HOLY CROSS |  | Granted | Y | 2021-03-16 | 1 | N | 2021-03-10 | N | 5 | N |  | N | 302735.38 | 624666.92 | 16:35
2021-10-26 12:29 | AD031 | 59631393/1 | WORKS STOP | 2021-10-22 | 2021-10-26 | 4 | WORKS CLOSED | 3 |  | N | NORFOLK COUNTY COUNCIL | SITE PERMANENT | ROAD CLOSURE | VISIBLY LEAKING COMMUNICATION PIPE | NORWICH ROAD | STOKE HOLY CROSS | CARRIAGEWAY TYPE 4 - UP TO 0.5 MS | ASSET ACTIVITY & REINSTATEMENT IF REQD | 1 | 3 | WORKS STOP | IMMEDIATE (URGENT) | SOUTH NORFOLK | CW | EXCAVATION WORKS - OTHER | Y | STOKE HOLY CROSS |  | Granted | Y | 2021-10-26 | 1 | Y | 2021-10-22 | N | 3 | N |  | N | 301746.13 | 623480.73 | 7:30
2021-12-08 14:38 | AD031 | 59792759 | WORKS STOP | 2021-12-01 | 2021-12-06 | 5 | WORKS CLOSED NOX | 4 |  | N | NORFOLK COUNTY COUNCIL | SITE ABANDONED | ROAD CLOSURE | visibly leaking communication pipe - occupation of road closure | CHANDLER ROAD | STOKE HOLY CROSS | CARRIAGEWAY TYPE 4 - UP TO 0.5 MS | ASSET ACTIVITY & REINSTATEMENT IF REQD | 2 | 7 | WORKS STOP | IMMEDIATE (URGENT) | SOUTH NORFOLK | CW | NO EXCAVATION WORKS - OTHER | N | STOKE HOLY CROSS |  | Granted | Y | 2021-12-06 | 1 | N | 2021-12-01 | N | 4 | N | 14 | N | 302722.21 | 624942.07 | 8:30
2021-12-10 10:39 | AD031 | 59792759/1 | WORKS STOP | 2021-12-09 | 2021-12-10 | 1 | WORKS CLOSED | 2 |  | N | NORFOLK COUNTY COUNCIL | SITE PERMANENT | ROAD CLOSURE | visibly leaking communication pipe | CHANDLER ROAD | STOKE HOLY CROSS | CARRIAGEWAY TYPE 4 - UP TO 0.5 MS | ASSET ACTIVITY & REINSTATEMENT IF REQD | 1 | 4 | WORKS STOP | IMMEDIATE (URGENT) | SOUTH NORFOLK | CW | EXCAVATION WORKS - OTHER | N | STOKE HOLY CROSS |  | Granted | Y | 2021-12-10 | 1 | N | 2021-12-09 | N | 2 | N |  | N | 302722.21 | 624942.07 | 8:00
2022-04-25 07:30 | AD031 | 60563028 | WORKS STOP | 2022-04-20 | 2022-04-23 | 3 | WORKS CLOSED | 3 |  | N | NORFOLK COUNTY COUNCIL | SITE PERMANENT | ROAD CLOSURE | Repair visibly leaking communication pipe | NORWICH ROAD | STOKE HOLY CROSS | CARRIAGEWAY TYPE 4 - UP TO 0.5 MS | ASSET ACTIVITY & REINSTATEMENT IF REQD | 1 | 3 | WORKS STOP | IMMEDIATE (URGENT) | SOUTH NORFOLK | CW | EXCAVATION WORKS - OTHER | Y | STOKE HOLY CROSS |  | Granted | Y | 2022-04-23 | 1 | Y | 2022-04-20 | N | 3 | N |  | N | 301744.8 | 623479.8 | 8:00
2022-04-26 13:23 | AD031 | 60589133 | WORKS STOP | 2022-04-25 | 2022-04-26 | 1 | WORKS CLOSED | 2 |  | N | NORFOLK COUNTY COUNCIL | SITE PERMANENT | ROAD CLOSURE | Repair burst water main | PORINGLAND ROAD | STOKE HOLY CROSS | CARRIAGEWAY TYPE 4 - UP TO 0.5 MS | ASSET ACTIVITY & REINSTATEMENT IF REQD | 1 | 4 | WORKS STOP | IMMEDIATE (URGENT) | SOUTH NORFOLK | CW | EXCAVATION WORKS - OTHER | Y | STOKE HOLY CROSS |  | Granted | Y | 2022-04-26 | 1 | Y | 2022-04-25 | N | 2 | N |  | N | 302609.53 | 625956.26 | 8:51
2022-08-02 15:51 | AD031 | 61015987 | WORKS STOP | 2022-07-28 | 2022-08-02 | 5 | WORKS CLOSED | 4 |  | N | NORFOLK COUNTY COUNCIL | SITE PERMANENT | ROAD CLOSURE | BURST MAIN | PORINGLAND ROAD | STOKE HOLY CROSS | CARRIAGEWAY TYPE 4 - UP TO 0.5 MS | ASSET ACTIVITY & REINSTATEMENT IF REQD | 1 | 2 | WORKS STOP | IMMEDIATE (URGENT) | SOUTH NORFOLK | CW | EXCAVATION WORKS - OTHER | Y | STOKE HOLY CROSS |  | Granted | Y | 2022-08-02 | 1 | Y | 2022-07-28 | N | 4 | N |  | N | 302580.24 | 625880.22 | 13:36
2022-12-15 08:02 | AD031 | 61646783 | WORKS STOP | 2022-12-12 | 2022-12-15 | 3 | WORKS CLOSED | 4 |  | N | NORFOLK COUNTY COUNCIL | SITE PERMANENT | ROAD CLOSURE | fix leak | LONG LANE | STOKE HOLY CROSS | CARRIAGEWAY TYPE 4 - UP TO 0.5 MS | ASSET ACTIVITY & REINSTATEMENT IF REQD | 1 | 4 | WORKS STOP | IMMEDIATE (URGENT) | SOUTH NORFOLK | CW | EXCAVATION WORKS - OTHER | Y | STOKE HOLY CROSS |  | Granted | Y | 2022-12-15 | 1 | Y | 2022-12-12 | N | 4 | N |  | N | 302118.71 | 624330.54 | 14:31
2022-12-28 07:09 | AD031 | 61673523 | WORKS STOP | 2022-12-22 | 2022-12-23 | 1 | WORKS CLOSED | 2 |  | N | NORFOLK COUNTY COUNCIL | SITE PERMANENT | ROAD CLOSURE | burst main | LONG LANE | STOKE HOLY CROSS | CARRIAGEWAY TYPE 4 - UP TO 0.5 MS | ASSET ACTIVITY & REINSTATEMENT IF REQD | 1 | 3 | WORKS STOP | IMMEDIATE (URGENT) | SOUTH NORFOLK | VG | EXCAVATION WORKS - OTHER | Y | STOKE HOLY CROSS |  | Granted | Y | 2022-12-23 | 1 | Y | 2022-12-22 | N | 2 | N |  | N | 302146.4 | 624475.92 | 7:15
2023-06-02 12:54 | AD031 | 62034055/1 | WORKS STOP | 2023-05-22 | 2023-05-27 | 5 | WORKS CLOSED | 5 |  | N | NORFOLK COUNTY COUNCIL | SITE PERMANENT | ROAD CLOSURE | visibly leaking stop tap | NORWICH ROAD | STOKE HOLY CROSS | CARRIAGEWAY TYPE 4 - UP TO 0.5 MS | ASSET ACTIVITY & REINSTATEMENT IF REQD | 1 | 3 | WORKS STOP | IMMEDIATE (URGENT) | SOUTH NORFOLK | FW | EXCAVATION WORKS - OTHER | Y | STOKE HOLY CROSS |  | Granted | Y | 2023-05-27 | 1 | Y | 2023-05-22 | N | 5 | N | 29 | N | 301631.73 | 623467.64 | 8:29
Formulas:
Date Diff = DAYS([End],[Start])

## Skewb
01- PERMIT REFERENCE NUMBER | 02- WORK REFERENCE NUMBER | 03 - START DATE | 04 - END DATE | Date Diff | 05- TOWN | 06- PERMIT STATUS | 07- WORK STATUS | 08- CONTRACTOR NAME | 09- USRN | 10 -ROAD CATEGORY | 11 -REASONABLE PERIOD END DATE | 12 -WORK CATEGORY | 13 -ACTIVITY TYPE | 14 -TRAFFIC SENSITIVE FLAG | 15 -STREET NAME | 16- TRAFFIC MANAGEMENT TYPE | 17- HIGHWAYAUTHORITY | 18- AD | 20- INTERNAL STATUS | 23- REGISTRATION DUE DATE | 24- ASSIGNED DATE | 28- FOLLOW UP DUE DATE | 30 - WORKS DESCRIPTION | 34 - ALTERATION CREATED DATE
AD03167703178_1-01 | AD03167703178_1 | 2026-03-17 07:00 | 2026-03-23 | 6 | STOKE HOLY CROSS | Granted | In Progress | IMR Norwich | 36001401 | Carriageway type 4 (up to 0.5 MSA) | 2026-03-23 | Immediate Urgent | Utility Repair And Maintenance Works | Yes | NORWICH ROAD | Road Closure | NORFOLK COUNTY COUNCIL | AD031 | UNASSIGNED |  |  | 2026-03-02 | Leaking comm pipe under 8ft hedge we will need to locate com in footway
AD03167814299-01 | AD03167814299 | 2026-03-10 14:32 | 2026-03-16 20:59 | 6 | STOKE HOLY CROSS | Closed | Completed | IMR Norwich | 36001114 | Carriageway type 4 (up to 0.5 MSA) | 2026-03-18 | Immediate Urgent | Utility Repair And Maintenance Works | Yes | LONG LANE | Road Closure | NORFOLK COUNTY COUNCIL | AD031 | UNASSIGNED | 2026-03-30 |  | 2026-02-23 | Excavate and repair leaking main | 2026-03-16
AD03167703178-01 | AD03167703178 | 2026-03-03 07:30 | 2026-03-03 13:59 | 0 | STOKE HOLY CROSS | Closed | Completed | IMR Norwich | 36001401 | Carriageway type 4 (up to 0.5 MSA) | 2026-03-06 | Immediate Urgent | Utility Repair And Maintenance Works | Yes | NORWICH ROAD | Road Closure | NORFOLK COUNTY COUNCIL | AD031 | AUTO_CLOSED | 2026-03-17 | 2026-03-03 | 2026-02-16 | leaking comms pipe
AD03167691506_1-01 | AD03167691506_1 | 2026-02-06 08:00 | 2026-02-12 14:47 | 6 | STOKE HOLY CROSS | Closed | Completed | IMR Norwich | 36001521 | Carriageway type 4 (up to 0.5 MSA) | 2026-02-12 | Immediate Urgent | Utility Repair And Maintenance Works | Yes | PORINGLAND ROAD | Road Closure | NORFOLK COUNTY COUNCIL | AD031 | UNASSIGNED | 2026-02-26 |  | 2026-01-22 | Burst main
AD03167559621-01 | AD03167559621 | 2026-01-15 10:15 | 2026-01-21 14:55 | 6 | STOKE HOLY CROSS | Closed | Completed | IMR Norwich | 36001114 | Carriageway type 4 (up to 0.5 MSA) | 2026-01-21 | Immediate Urgent | Utility Repair And Maintenance Works | Yes | LONG LANE | Road Closure | NORFOLK COUNTY COUNCIL | AD031 | UNASSIGNED | 2026-02-04 |  | 2025-12-30 | Excavate and carry out repairs to a visibly leaking water main.
AD03166442786-01 | AD03166442786 | 2025-07-04 09:30 | 2025-07-10 23:19 | 6 | STOKE HOLY CROSS | Closed | Completed | IMR Norwich | 36001114 | Carriageway type 4 (up to 0.5 MSA) | 2025-07-10 | Immediate Urgent | Utility Repair And Maintenance Works | Yes | LONG LANE | Road Closure | NORFOLK COUNTY COUNCIL | AD031 | UNASSIGNED | 2025-07-24 |  | 2025-06-19 | visible leak on main
AD03165825427-01 | AD03165825427 | 2025-03-05 16:30 | 2025-03-11 20:38 | 6 | STOKE HOLY CROSS | Closed | Completed | IMR Norwich | 36001114 | Carriageway type 4 (up to 0.5 MSA) | 2025-03-11 | Immediate Urgent | Utility Repair And Maintenance Works | Yes | LONG LANE | Road Closure | NORFOLK COUNTY COUNCIL | AD031 | UNASSIGNED | 2025-03-25 |  | 2025-02-18 | repair leak on 4" ci main
AD03165466549-01 | AD03165466549 | 2025-01-17 11:00 | 2025-01-22 12:18 | 5 | STOKE HOLY CROSS | Closed | Completed | IMR Norwich | 36001114 | Carriageway type 4 (up to 0.5 MSA) | 2025-01-23 | Immediate Urgent | Utility Repair And Maintenance Works | Yes | LONG LANE | Road Closure | NORFOLK COUNTY COUNCIL | AD031 | UNASSIGNED | 2025-02-05 |  | 2025-01-02 | visible leak on main
AD03165477770-01 | AD03165477770 | 2025-01-11 14:32 | 2025-01-16 20:09 | 5 | STOKE HOLY CROSS | Closed | Completed | IMR Norwich | 36000303 | Carriageway type 4 (up to 0.5 MSA) | 2025-01-17 | Immediate Emergency | Utility Repair And Maintenance Works | No | CHANDLER ROAD | Road Closure | NORFOLK COUNTY COUNCIL | AD031 | UNASSIGNED | 2025-01-30 |  | 2024-12-24 | burst main
AD03164788383-02 | AD03164788383 | 2024-10-24 07:30 | 2024-10-25 13:47 | 1 | STOKE HOLY CROSS | Closed | Completed | IMR Norwich | 36001401 | Carriageway type 4 (up to 0.5 MSA) | 2024-10-28 | Immediate Urgent | Utility Repair And Maintenance Works | Yes | NORWICH ROAD | Road Closure | NORFOLK COUNTY COUNCIL | AD031 | UNASSIGNED | 2024-11-08 |  | 2024-10-09 | visible leak on communication pipe
AD03164840372-01 | AD03164840372 | 2024-10-09 07:30 | 2024-10-14 10:03 | 5 | STOKE HOLY CROSS | Closed | Completed | IMR Norwich | 36000303 | Carriageway type 4 (up to 0.5 MSA) | 2024-10-15 | Immediate Urgent | Utility Repair And Maintenance Works | No | CHANDLER ROAD | Road Closure | NORFOLK COUNTY COUNCIL | AD031 | UNASSIGNED | 2024-10-28 |  | 2024-09-24 | repair leaking communication pipe
AD03164323104-01 | AD03164323104 | 2024-07-29 07:30 | 2024-07-30 18:25 | 1 | STOKE HOLY CROSS | Closed | Completed | IMR Norwich | 36001401 | Carriageway type 4 (up to 0.5 MSA) | 2024-08-02 | Immediate Urgent | Utility Repair And Maintenance Works | Yes | NORWICH ROAD | Road Closure | NORFOLK COUNTY COUNCIL | AD031 | UNASSIGNED | 2024-08-13 |  | 2024-07-12 | Leaking stop tap