## Guidance
Guidance
This page should be read before completing the workbook.
The purpose of this workbook is to allow Ofwat to understand latest view of total development costs for AMP8 onwards and compare this against the expenditure that has taken place for the current gate.
There are two sheets for development cost and expenditure profile. The sheets labelled as 'Development Cost Existing' and 'Expenditure Profile Existing' refers to the original gate categories (Gate 1, Gate 2 etc..).
This should be completed if the SRO project is still using the existing gated process labels.
SRO projects using the new combined gated process should use the standard 'Development Cost' and 'Expenditure Profile' tabs.
All expenditure must be reported in £ millions to a minimum of 3 decimal places and presented in the 2022–23 price base. For any figures that need converting, please use the ONS construction output price indicies.
Please read the guidance for the various categories of development expenditure under 'Category Guidance' tab before proceeding to completing the templates.
1. Development Cost
This sheet is a blank Expenditure by AMP templates (provided as part of the PR24 request). This should be populated with the latest forecast of spend for the project from AMP8 onwards only.
To support this data, please explain any changes with the following information as a minimum within the commentary column provided:
▸ | Which costs which have increased since the final determinations and the key drivers for this?
▸ | Which costs have been reprofiled from future gates?
▸ | Which costs are newly identified costs and therefore have not been budgeted for for previously?
▸ | Which cost have been carried over? For example, those which have been subject to delays and prevented planned AMP7 activities which are now being required in AMP8.
▸ | An explantion of what the costs are if they are allocated in the 'Other' category. Please include a breakdown of the 'Other' costs where possible.
2. Expenditure Profile
This is a supporting sheet which captures the entire view of expenditure across the project (also provided as part of the PR24 request).
Please populate from early construction/enabling works onwards (development expenditure is automatically calculated), including an explantion of what the costs are if they are allocated in the 'Other expenditure' line.
Please also populate the 'SRO Cost Overview' table with the latest view of forecasts, and any supporting commentary you may have.
3. Efficiency of Expenditure
This sheet should be populated in accordance with the gate guidance, using the latest expenditure for the current gate for each category.
Click on the drop down on the cell highlighted yellow (B4) to select the relevant gate. This contains both types of gates from the existing process and new combined gated process.
To support the data, commentary should be provided under the 'Description of Activity' cell.

## Category Guidance
Category Guidance
| Category | Guidance
| Programme & Project Management (inc. Assurance) | Detail costs for all activities associated with programme management and governance, day-to-day project management (including costs for any external project managers utilised), and assurance.
| Engineering, Design and Ground Investigations | Detail all costs for activities associated with undertaking a feasibility assessment, engineering, concept design, site selection and process selection. This section should only include site specific ground investigations.
| Option benefits, development and appraisal | Detail costs for all activities associated with development of the options benefits and impacts (water resource, carbon, and wider best value, plus direct costs associated with the appraisal of the option against sub-options or alternatives (excluding that carried out at the strategic level for the WRMP). Relevant assessments should be consistent with the water resources planning guidelines for 2024.
| Environmental and supporting assessments (inc. Data Sampling, EIA, HRA, transport and utilities assessments) | Detail costs for all environmental assessments and activities including Biodiversity Net Gain. This should include data collection and sampling but not ground investigations (above). Include regulator costs for the Environment Agency and Natural England.
| Other Data Collection, Sampling, and Pilot Trials | This section should include any data collection and sampling excluding those carried out for planning and environmental assessments.
| Stakeholder Engagement | Detail costs for all activities associated with customer and stakeholder engagement related to the solution (not covered elsewhere).
| Planning | All costs associated with development of a planning and consenting strategy, pre-application advice, liaison, policy review, assessments review, planning statement, submission and post submission activity.
| Legal | Detail costs associated with any legal activities related to the solution.
| Other | Detail costs associated with any other activities relevant to solution development for the relevant gate that is not covered in the above categories. Please ensure these activities are clearly explained.
| Commercial and Procurement - Strategy | Detail costs for any activities associated with developing the commercial and procurement strategies.
| Commercial and Procurement - ECI | Detail costs for any activities associated with Early Contractor Involvement (ECI).
| Land | All activities associated with land identification, referencing, negotiations and acquisition (excluding legal and including land related Biodiversity Net Gain costs if relevant).
| Enabling Works | All activities associated with enabling works excluding the activities (e.g. planning and environmental assessments) included above.

## Development Cost (hidden)
Development Expenditure (£m)
SRO Name
| Gate | Main Category | Sub-Category | Pre-2025 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Post 2030 | Total | Commentary
| Gate A | Core Development Cost | Programme & Project Management (inc. Assurance) | [7 empty] | 0
| Gate A | Core Development Cost | Engineering, Design and Ground Investigations | [7 empty] | 0
| Gate A | Core Development Cost | Option benefits, development and appraisal | [7 empty] | 0
| Gate A | Core Development Cost | Environmental and supporting assessments (inc. Data Sampling, EIA, HRA, transport and utilities assessments) | [7 empty] | 0
| Gate A | Core Development Cost | Other Data Collection, Sampling, and Pilot Trials | [7 empty] | 0
| Gate A | Core Development Cost | Stakeholder Engagement | [7 empty] | 0
| Gate A | Core Development Cost | Planning | [7 empty] | 0
| Gate A | Core Development Cost | Legal | [7 empty] | 0
| Gate A | Core Development Cost | Other | [7 empty] | 0 | Explanation required
| Gate A | Commercial and Procurement | Commercial and Procurement - Strategy | [7 empty] | 0
| Gate A | Commercial and Procurement | Commercial and Procurement - ECI | [7 empty] | 0
| Gate A | Land & Enabling | Land | [7 empty] | 0
| Gate A | Land & Enabling | Enabling Works | [7 empty] | 0
| Gate A | Total Cost | Gate A Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gate B | Core Development Cost | Programme & Project Management (inc. Assurance) | [7 empty] | 0
| Gate B | Core Development Cost | Engineering, Design and Ground Investigations | [7 empty] | 0
| Gate B | Core Development Cost | Option benefits, development and appraisal | [7 empty] | 0
| Gate B | Core Development Cost | Environmental and supporting assessments (inc. Data Sampling, EIA, HRA, transport and utilities assessments) | [7 empty] | 0
| Gate B | Core Development Cost | Other Data Collection, Sampling, and Pilot Trials | [7 empty] | 0
| Gate B | Core Development Cost | Stakeholder Engagement | [7 empty] | 0
| Gate B | Core Development Cost | Planning | [7 empty] | 0
| Gate B | Core Development Cost | Legal | [7 empty] | 0
| Gate B | Core Development Cost | Other | [7 empty] | 0 | Explanation required
| Gate B | Commercial and Procurement | Commercial and Procurement - Strategy | [7 empty] | 0
| Gate B | Commercial and Procurement | Commercial and Procurement - ECI | [7 empty] | 0
| Gate B | Land & Enabling | Land | [7 empty] | 0
| Gate B | Land & Enabling | Enabling Works | [7 empty] | 0
| Gate B | Total Cost | Gate B Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gate C | Core Development Cost | Programme & Project Management (inc. Assurance) | [7 empty] | 0
| Gate C | Core Development Cost | Engineering, Design and Ground Investigations | [7 empty] | 0
| Gate C | Core Development Cost | Option benefits, development and appraisal | [7 empty] | 0
| Gate C | Core Development Cost | Environmental and supporting assessments (inc. Data Sampling, EIA, HRA, transport and utilities assessments) | [7 empty] | 0
| Gate C | Core Development Cost | Other Data Collection, Sampling, and Pilot Trials | [7 empty] | 0
| Gate C | Core Development Cost | Stakeholder Engagement | [7 empty] | 0
| Gate C | Core Development Cost | Planning | [7 empty] | 0
| Gate C | Core Development Cost | Legal | [7 empty] | 0
| Gate C | Core Development Cost | Other | [7 empty] | 0 | Explanation required
| Gate C | Commercial and Procurement | Commercial and Procurement - Strategy | [7 empty] | 0
| Gate C | Commercial and Procurement | Commercial and Procurement - ECI | [7 empty] | 0
| Gate C | Land & Enabling | Land | [7 empty] | 0
| Gate C | Land & Enabling | Enabling Works | [7 empty] | 0
| Gate C | Total Cost | Gate C Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gate D | Core Development Cost | Programme & Project Management (inc. Assurance) | [7 empty] | 0
| Gate D | Core Development Cost | Engineering, Design and Ground Investigations | [7 empty] | 0
| Gate D | Core Development Cost | Option benefits, development and appraisal | [7 empty] | 0
| Gate D | Core Development Cost | Environmental and supporting assessments (inc. Data Sampling, EIA, HRA, transport and utilities assessments) | [7 empty] | 0
| Gate D | Core Development Cost | Other Data Collection, Sampling, and Pilot Trials | [7 empty] | 0
| Gate D | Core Development Cost | Stakeholder Engagement | [7 empty] | 0
| Gate D | Core Development Cost | Planning | [7 empty] | 0
| Gate D | Core Development Cost | Legal | [7 empty] | 0
| Gate D | Core Development Cost | Other | [7 empty] | 0 | Explanation required
| Gate D | Commercial and Procurement | Commercial and Procurement - Strategy | [7 empty] | 0
| Gate D | Commercial and Procurement | Commercial and Procurement - ECI | [7 empty] | 0
| Gate D | Land & Enabling | Land | [7 empty] | 0
| Gate D | Land & Enabling | Enabling Works | [7 empty] | 0
| Gate D | Total Cost | Gate D Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Expenditure Profile (hidden)
Expenditure Profile (£m)
SRO Name
| Category | 2020-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2025-30 | 2030-35 | 2035-40 | 2040-45 | 2045-50 | 2020-50 | Commentary
Development expenditure (minus land&enabling works)
| - Gate A | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Gate B | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Gate C | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Gate D | 0 | 0 | 0 | 0 | 0 | 0 | 0
Early construction/enabling works
| - Capex | [6 empty] | 0
| - Opex | [6 empty] | 0
Main works expenditure
| - Capex | [6 empty] | 0
| - Opex | [6 empty] | 0
Associated development expenditure
| - Capex - Land & Property | [6 empty] | 0
| - Opex | [6 empty] | 0
Other expenditure
| - Capex | [6 empty] | 0
| - Opex | [6 empty] | 0
Total expenditure
| - Capex | [6 empty] | 0
| - Opex | [6 empty] | 0
| SRO Cost Overview |  | Commentary
Base Capex (£m)
Risk (£m)
Optimism Bias (£m)
Total Capex (£m)
Fixed Opex (£m)
Variable Opex (£m)
Annual Opex (£m)
Asset Life (yrs)
Total Opex (£m)
Wholelife Cost (£m)
Benefit (Ml/d)

## Development Cost Existing
Development Expenditure (£m)
| SRO Name | Norfolk (Bacton) Desalination
Note - This expenditure profile is consistent with the information submitted at PR24. Given the early stage of project maturity, updated cost estimates are not yet available. As such, the profile does not fully align with the programme detail presented in the Gate 1 report, reflecting the inherent uncertainty in forecasting development-phase expenditure at this stage. Cost splits aligned to the September 2024 RAPID submission, with adjustments made to reflect the updated Ofwat template structure. This includes deriving Gate 2 splits, consolidating post-Gate 4 categories, redistributing allocations where sub-categories have changed, and setting new categories to zero where no prior allocation existed.
| Gate | Main Category | Sub-Category | Pre-2025 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Post 2030 | Total | Commentary
| Gate 1 | Core Development Cost | Programme & Project Management (inc. Assurance) | 0 | 0.35688 | 0.066874 | 0 | 0 | 0 | 0 | 0.42375
| Gate 1 | Core Development Cost | Engineering, Design and Ground Investigations | 0 | 0.45146 | 0.24899 | 0 | 0 | 0 | 0 | 0.70045
| Gate 1 | Core Development Cost | Option benefits, development and appraisal | 0 | 0.27045 | 0.081343 | 0 | 0 | 0 | 0 | 0.35179
| Gate 1 | Core Development Cost | Environmental and supporting assessments (inc. Data Sampling, EIA, HRA, transport and utilities assessments) | 0 | 0.19407 | 0.03038 | 0 | 0 | 0 | 0 | 0.22445
| Gate 1 | Core Development Cost | Other Data Collection, Sampling, and Pilot Trials | 0 | 0.49108 | 0 | 0 | 0 | 0 | 0 | 0.49108
| Gate 1 | Core Development Cost | Stakeholder Engagement | 0 | 0.1297 | 0.050946 | 0 | 0 | 0 | 0 | 0.18065
| Gate 1 | Core Development Cost | Planning | 0 | 0.007441 | 0.0036064 | 0 | 0 | 0 | 0 | 0.011047
| Gate 1 | Core Development Cost | Legal | 0 | 0.031182 | 0.0056342 | 0 | 0 | 0 | 0 | 0.036817
| Gate 1 | Core Development Cost | Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gate 1 | Commercial and Procurement | Commercial and Procurement - Strategy | 0 | 0.31405 | 0.091246 | 0 | 0 | 0 | 0 | 0.4053
| Gate 1 | Commercial and Procurement | Commercial and Procurement - ECI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gate 1 | Land & Enabling | Land | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gate 1 | Land & Enabling | Enabling Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gate 1 | Total Cost | Gate 1 Total | 0 | 2.2463 | 0.57902 | 0 | 0 | 0 | 0 | 2.8253 | The Gate 1 efficiency has been proportionately distributed across future gates, reflecting the expectation that these planned costs will materialise in later stages.
| Gate 2 | Core Development Cost | Programme & Project Management (inc. Assurance) | 0 | 0.048267 | 0.1448 | 0 | 0 | 0 | 0 | 0.19307
| Gate 2 | Core Development Cost | Engineering, Design and Ground Investigations | 0 | 0.12067 | 0.362 | 0 | 0 | 0 | 0 | 0.48267
| Gate 2 | Core Development Cost | Option benefits, development and appraisal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gate 2 | Core Development Cost | Environmental and supporting assessments (inc. Data Sampling, EIA, HRA, transport and utilities assessments) | 0 | 0.12067 | 0.362 | 0 | 0 | 0 | 0 | 0.48267
| Gate 2 | Core Development Cost | Other Data Collection, Sampling, and Pilot Trials | 0 | 0.12067 | 0.362 | 0 | 0 | 0 | 0 | 0.48267
| Gate 2 | Core Development Cost | Stakeholder Engagement | 0 | 0.0362 | 0.1086 | 0 | 0 | 0 | 0 | 0.1448
| Gate 2 | Core Development Cost | Planning | 0 | 0.0362 | 0.1086 | 0 | 0 | 0 | 0 | 0.1448
| Gate 2 | Core Development Cost | Legal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gate 2 | Core Development Cost | Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gate 2 | Commercial and Procurement | Commercial and Procurement - Strategy | 0 | 0.19066 | 0.57199 | 0 | 0 | 0 | 0 | 0.76265
| Gate 2 | Commercial and Procurement | Commercial and Procurement - ECI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gate 2 | Land & Enabling | Land | 0 | 0.1967 | 0.5901 | 0 | 0 | 0 | 0 | 0.7868
| Gate 2 | Land & Enabling | Enabling Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gate 2 | Total Cost | Gate 2 Total | 0 | 0.87003 | 2.6101 | 0 | 0 | 0 | 0 | 3.4801
| Gate 3 | Core Development Cost | Programme & Project Management (inc. Assurance) | 0 | 0 | 0.68405 | 2.0521 | 0 | 0 | 0 | 2.7362
| Gate 3 | Core Development Cost | Engineering, Design and Ground Investigations | 0 | 0 | 0.91207 | 2.7362 | 0 | 0 | 0 | 3.6483
| Gate 3 | Core Development Cost | Option benefits, development and appraisal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gate 3 | Core Development Cost | Environmental and supporting assessments (inc. Data Sampling, EIA, HRA, transport and utilities assessments) | 0 | 0 | 0.72965 | 2.189 | 0 | 0 | 0 | 2.9186
| Gate 3 | Core Development Cost | Other Data Collection, Sampling, and Pilot Trials | 0 | 0 | 0.45603 | 1.3681 | 0 | 0 | 0 | 1.8241
| Gate 3 | Core Development Cost | Stakeholder Engagement | 0 | 0 | 0.27362 | 0.82086 | 0 | 0 | 0 | 1.0945
| Gate 3 | Core Development Cost | Planning | 0 | 0 | 0.27362 | 0.82086 | 0 | 0 | 0 | 1.0945
| Gate 3 | Core Development Cost | Legal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gate 3 | Core Development Cost | Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gate 3 | Commercial and Procurement | Commercial and Procurement - Strategy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gate 3 | Commercial and Procurement | Commercial and Procurement - ECI | 0 | 0 | 1.315 | 3.9451 | 0 | 0 | 0 | 5.2601
| Gate 3 | Land & Enabling | Land | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gate 3 | Land & Enabling | Enabling Works | 0 | 0 | 1.3567 | 4.07 | 0 | 0 | 0 | 5.4267
| Gate 3 | Total Cost | Gate 3 Total | 0 | 0 | 6.0007 | 18.0022 | 0 | 0 | 0 | 24.0029
| Gate 4 | Core Development Cost | Programme & Project Management (inc. Assurance) | 0 | 0 | 0 | 0.76702 | 2.3011 | 0 | 0 | 3.0681
| Gate 4 | Core Development Cost | Engineering, Design and Ground Investigations | 0 | 0 | 0 | 1.0227 | 3.0681 | 0 | 0 | 4.0908
| Gate 4 | Core Development Cost | Option benefits, development and appraisal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gate 4 | Core Development Cost | Environmental and supporting assessments (inc. Data Sampling, EIA, HRA, transport and utilities assessments) | 0 | 0 | 0 | 0.61362 | 1.8408 | 0 | 0 | 2.4545
| Gate 4 | Core Development Cost | Other Data Collection, Sampling, and Pilot Trials | 0 | 0 | 0 | 0.40908 | 1.2272 | 0 | 0 | 1.6363
| Gate 4 | Core Development Cost | Stakeholder Engagement | 0 | 0 | 0 | 0.25567 | 0.76702 | 0 | 0 | 1.0227
| Gate 4 | Core Development Cost | Planning | 0 | 0 | 0 | 0.25567 | 0.76702 | 0 | 0 | 1.0227
| Gate 4 | Core Development Cost | Legal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gate 4 | Core Development Cost | Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gate 4 | Commercial and Procurement | Commercial and Procurement - Strategy | 0 | 0 | 0 | 1.3129 | 3.9388 | 0 | 0 | 5.2518
| Gate 4 | Commercial and Procurement | Commercial and Procurement - ECI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gate 4 | Land & Enabling | Land | 0 | 0 | 0 | 0.90301 | 2.709 | 0 | 0 | 3.612
| Gate 4 | Land & Enabling | Enabling Works | 0 | 0 | 0 | 0.4515 | 1.3545 | 0 | 0 | 1.806
| Gate 4 | Total Cost | Gate 4 Total | 0 | 0 | 0 | 5.9912 | 17.9736 | 0 | 0 | 23.9648
| Post Gate 4 | Core Development Cost | Programme & Project Management (inc. Assurance) | 0 | 0 | 0 | 0 | 0.98891 | 2.9667 | 0 | 3.9557
| Post Gate 4 | Core Development Cost | Engineering, Design and Ground Investigations | 0 | 0 | 0 | 0 | 0.64279 | 1.9284 | 0 | 2.5712
| Post Gate 4 | Core Development Cost | Option benefits, development and appraisal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Post Gate 4 | Core Development Cost | Environmental and supporting assessments (inc. Data Sampling, EIA, HRA, transport and utilities assessments) | 0 | 0 | 0 | 0 | 0.29667 | 0.89002 | 0 | 1.1867
| Post Gate 4 | Core Development Cost | Other Data Collection, Sampling, and Pilot Trials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Post Gate 4 | Core Development Cost | Stakeholder Engagement | 0 | 0 | 0 | 0 | 0.61807 | 1.8542 | 0 | 2.4723
| Post Gate 4 | Core Development Cost | Planning | 0 | 0 | 0 | 0 | 0.61807 | 1.8542 | 0 | 2.4723
| Post Gate 4 | Core Development Cost | Legal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Post Gate 4 | Core Development Cost | Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Post Gate 4 | Commercial and Procurement | Commercial and Procurement - Strategy | 0 | 0 | 0 | 0 | 1.25 | 3.7501 | 0 | 5.0002
| Post Gate 4 | Commercial and Procurement | Commercial and Procurement - ECI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Post Gate 4 | Land & Enabling | Land | 0 | 0 | 0 | 0 | 0.44252 | 1.3276 | 0 | 1.7701
| Post Gate 4 | Land & Enabling | Enabling Works | 0 | 0 | 0 | 0 | 0.8471 | 2.5413 | 0 | 3.3884
| Post Gate 4 | Total Cost | Post Gate 4 Total | 0 | 0 | 0 | 0 | 5.7042 | 17.1126 | 0 | 22.8167

## Expenditure Profile Existing
Expenditure Profile (£m)
| SRO Name | Norfolk (Bacton) Desalination
Note - This expenditure profile is consistent with the information submitted at PR24. Given the early stage of project maturity, updated cost estimates are not yet available. As such, the profile does not fully align with the programme detail presented in the Gate 1 report, reflecting the inherent uncertainty in forecasting development-phase expenditure at this stage.
| Category | 2020-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2025-30 | 2030-35 | 2035-40 | 2040-45 | 2045-50 | 2020-50 | Commentary
Development expenditure (minus land&enabling works)
| - Gate 1 | 0 | 2.2463 | 0.57902 | 0 | 0 | 0 | 2.8253 | [5 empty] | The Gate 1 efficiency has been proportionately distributed across future gates, reflecting the expectation that these planned costs will materialise in later stages.
| - Gate 2 | 0 | 0.67333 | 2.02 | 0 | 0 | 0 | 2.6933
| - Gate 3 | 0 | 0 | 4.6441 | 13.9322 | 0 | 0 | 18.5763
| - Gate 4 | 0 | 0 | 0 | 4.6367 | 13.9101 | 0 | 18.5468
| - Post Gate 4 to Main works award | 0 | 0 | 0 | 0 | 4.4146 | 13.2437 | 17.6583
Early construction/enabling works
| - Capex | 0 | 0 | 1.3567 | 4.5215 | 2.2016 | 2.5413 | 10.6211
| - Opex | [6 empty] | 0
Main works expenditure
| - Capex | [6 empty] | 0 | 727
| - Opex | [6 empty] | 0 |  | 134.1911 | 134.1911 | 134.1911
Associated development expenditure
| - Capex - Land & Property | 0 | 0.1967 | 0.5901 | 0.90301 | 3.1515 | 1.3276 | 6.1689 | [5 empty] | Note: This only covers land sub-category under Land & Enabling Works main category
| - Opex | [6 empty] | 0
Other expenditure
| - Capex | [6 empty] | 0
| - Opex | [6 empty] | 0
Total base expenditure
| - Capex |  | 3.1164 | 9.1899 | 23.9934 | 23.6778 | 17.1126 | 77.09 | 727 | 0 | 0 | 0 | 0
| - Opex |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134.1911 | 134.1911 | 134.1911 | 0
| SRO Cost Overview |  | Commentary
| Base Capex (£m) | 726.644 | Taken from information submitted for PR24 in response to OFW-REP-ANH-025
| Risk (£m) | - | Not explicitly stated in PR24 submission
| Optimism Bias (£m) | - | Not explicitly stated in PR24 submission
| Total Capex (£m) | 1046.601 | Taken from information submitted for PR24 in response to OFW-REP-ANH-025
| Fixed Opex (£m) | - | Not explicitly stated in PR24 submission
| Variable Opex (£m) | - | Not explicitly stated in PR24 submission
| Annual Opex (£m) | - | Not explicitly stated in PR24 submission
| Asset Life (yrs) | - | Not explicitly stated in PR24 submission
| Total Opex (£m) | 402.573 | Taken from information submitted for PR24 in response to OFW-REP-ANH-025
| Wholelife Cost (£m) | - | Not explicitly stated in PR24 submission
| Benefit (Ml/d) | 60

## Efficiency of Expenditure
Efficiency of Expenditure (£)
Select Gate below
| Gate 1 | Efficiency of Expenditure Template
| SRO Name | Norfolk (Bacton) Desalination
| Main Category | Sub-Category | Activity | Expenditure £, 2022-23 prices | [6 empty] | Activity % of Total Expenditure | Activity Allowance AMP8 | Remaining | Description of Activity
|  |  |  | Pre-2025 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Activity Total AMP8
|  | Programme & Project Management (inc. Assurance) | Project Controls | Expenditure £, 2022-23 prices 2025-26: 97314.07; Expenditure £, 2022-23 prices 2026-27: 9046.99 | 106361.06 | 3.765% |  |  | PMO and programme controls activities, including planning, reporting, and performance monitoring.
|  |  | Staff Costs | Expenditure £, 2022-23 prices 2025-26: 178063.2; Expenditure £, 2022-23 prices 2026-27: 31290.07 | 209353.27 | 7.41% |  |  | Senior leadership input, programme and project management, and associated support roles
|  |  | Advisory Services | Expenditure £, 2022-23 prices 2025-26: 69692.25; Expenditure £, 2022-23 prices 2026-27: 26536.85 | 96229.1 | 3.406% |  |  | Desalination strategic expertise to inform programme strategy and direction, plus third party assurance
|  |  | Total | 0 | 345069.52 | 66873.91 | 0 | 0 | 0 | 411943.43 | 14.58% |  | -411943.43
|  | Engineering, Design and Ground Investigations | Research & Advisory | Expenditure £, 2022-23 prices 2025-26: 148850.85; Expenditure £, 2022-23 prices 2026-27: 39176.81 | 188027.66 | 6.655% |  |  | Technical research and advisory activities to support source water characterisation, marine planning, and site selection.
|  |  | Coastal Monitoring Management | Expenditure £, 2022-23 prices 2025-26: 131816.36; Expenditure £, 2022-23 prices 2026-27: 11704.74 | 143521.1 | 5.08% |  |  | Management and coordination of coastal monitoring and sampling activities
|  |  | Intake and Outfall Strategy Development | Expenditure £, 2022-23 prices 2025-26: 52143.97; Expenditure £, 2022-23 prices 2026-27: 13943.92 | 66087.89 | 2.339% |  |  | Technical assessment activities to inform intake and outfall strategy, including consideration of best practice and regional application.
|  |  | Design Development | Expenditure £, 2022-23 prices 2025-26: 63963.56; Expenditure £, 2022-23 prices 2026-27: 142458.77 | 206422.33 | 7.306% |  |  | Mobilisation of early-stage design, including technical input, delivery planning, and site selection support.
|  |  | Blending Ratio Strategy | Expenditure £, 2022-23 prices 2025-26: 57245.19; Expenditure £, 2022-23 prices 2026-27: 41707.75 | 98952.94 | 3.502% |  |  | Consultancy and academia assessment of blending scenarios to inform WRMP modelling.
|  |  | Total | 0 | 454019.93 | 248991.99 | 0 | 0 | 0 | 703011.92 | 24.88% |  | -703011.92
|  | Option benefits, development and appraisal | Water Resources Investigations & Modelling | Expenditure £, 2022-23 prices 2025-26: 270451; Expenditure £, 2022-23 prices 2026-27: 81343.09 | 351794.09 | 12.45% |  |  | Technical investigations and modelling activities to inform and refine the water resources needs case.
[10 empty] | 0 | 0%
|  |  | Total | 0 | 270451 | 81343.09 | 0 | 0 | 0 | 351794.09 | 12.45% |  | -351794.09
|  | Environmental and supporting assessments (inc. Data Sampling, EIA, HRA, transport and utilities assessments) | Environmental Strategy and Planning | Expenditure £, 2022-23 prices 2025-26: 121642.22; Expenditure £, 2022-23 prices 2026-27: 20525.17 | 142167.39 | 5.032% |  |  | Technical activities to assess the feasibility of a pilot plant to support development of desalination solution.
|  |  | Site Selection | Expenditure £, 2022-23 prices 2025-26: 79411.01; Expenditure £, 2022-23 prices 2026-27: 9854.91 | 89265.92 | 3.159% |  |  | Coastal monitoring and sampling activities to inform water quality assessment, blending considerations, and design development.
[10 empty] | 0 | 0%
|  |  | Total | 0 | 201053.23 | 30380.08 | 0 | 0 | 0 | 231433.31 | 8.191% |  | -231433.31
|  | Other Data Collection, Sampling, and Pilot Trials | Pilot Plant Feasibility and Assessment | Expenditure £, 2022-23 prices 2025-26: 65495.78 | 65495.78 | 2.318% |  |  | Technical activities to assess the feasibility of a pilot plant to support development of desalination solution.
|  |  | Coastal Monitoring | Expenditure £, 2022-23 prices 2025-26: 425585.97 | 425585.97 | 15.06% |  |  | Coastal monitoring and sampling activities to inform water quality risk assessment, blending considerations, and design development.
|  |  | Total | 0 | 491081.75 | 0 | 0 | 0 | 0 | 491081.75 | 17.38% |  | -491081.75
|  | Stakeholder Engagement | Stakeholder Engagement | Expenditure £, 2022-23 prices 2025-26: 75007.53; Expenditure £, 2022-23 prices 2026-27: 34272.71 | 109280.24 | 3.868% |  |  | Stakeholder engagement activities to support development of the programme, including engagement planning and coordination of stakeholder interactions.
|  |  | National Appraisal Unit (NAU) | Expenditure £, 2022-23 prices 2025-26: 56959.49; Expenditure £, 2022-23 prices 2026-27: 16672.96 | 73632.45 | 2.606% |  |  | Activities associated with engagement with the National Appraisal Unit to support appraisal and assurance processes.
|  |  | Total | 0 | 131967.02 | 50945.67 | 0 | 0 | 0 | 182912.69 | 6.474% |  | -182912.69
|  | Planning | Planning & Consents | Expenditure £, 2022-23 prices 2025-26: 7440.96; Expenditure £, 2022-23 prices 2026-27: 3606.42 | 11047.38 | 0.391% |  |  | Activities to support planning and consenting, including development and refinement of the programme’s consenting strategy.
|  |  | Total | 0 | 7440.96 | 3606.42 | 0 | 0 | 0 | 11047.38 | 0.391% |  | -11047.38
|  | Legal | Legal Support Services | Expenditure £, 2022-23 prices 2025-26: 31182.36; Expenditure £, 2022-23 prices 2026-27: 5634.22 | 36816.58 | 1.303% |  |  | Legal and commercial advisory activities to support site selection and programme development, including review of relevant agreements and requirements.
|  |  | Total | 0 | 31182.36 | 5634.22 | 0 | 0 | 0 | 36816.58 | 1.303% |  | -36816.58
|  | Other | N/A | [6 empty] | 0 | 0%
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0
| Commercial and Procurement | Commercial and Procurement ECI | N/A | [6 empty] | 0 | 0%
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0
|  | Commercial and Procurement Strategy | Commercial & Procurement | Expenditure £, 2022-23 prices 2025-26: 86381.04; Expenditure £, 2022-23 prices 2026-27: 10426.29 | 96807.33 | 3.426% |  |  | Activities to support commercial and procurement management, including planning, coordination, and oversight of procurement processes.
|  |  | Commercial Services | Expenditure £, 2022-23 prices 2025-26: 107280.62; Expenditure £, 2022-23 prices 2026-27: 25890.55 | 133171.17 | 4.713% |  |  | Commercial advisory activities to support programme development, including commercial input to planning and decision-making.
|  |  | DPC Procurement Strategy | Expenditure £, 2022-23 prices 2025-26: 120388.2; Expenditure £, 2022-23 prices 2026-27: 54928.87 | 175317.07 | 6.205% |  |  | Activities to support development of the Direct Procurement for Customers (DPC) strategy.
|  |  | Total | 0 | 314049.86 | 91245.71 | 0 | 0 | 0 | 405295.57 | 14.35% |  | -405295.57
| Land & Enabling | Land | N/A | [6 empty] | 0 | 0%
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0
|  | Enabling Works | N/A | [6 empty] | 0 | 0%
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0
|  | Total | 0 | 0 | 2246315.63 | 579021.09 | 0 | 0 | 0 | 2825336.72 | 100% | 0 | -2825336.72 | 0
|  | Gate 1 Allowance | [7 empty] | 7709177 | bar: Expenditure £, 2022-23 prices Pre-2025 to Expenditure £, 2022-23 prices 2026-27
|  | Gate Under/Overspend |  | Expenditure £, 2022-23 prices Pre-2025: 0 | -4883840.28

## Data Validation (hidden)
Gate 1
Gate 2
Gate 3
Gate 4
Post Gate 4
Gate A
Gate B
Gate C
Gate D